## Task Tracking
Type | Change | Description | Est. Time | Actual Time | Team Member | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Critical | Implement gridded movement system into the main branch | Use Tim's grid engine, must breif team on how to effectively use it when constructing levels | 8 | 9 | Tim | Started | Started | Complete (Working) | - | - | - | - | - | - | - | - | -
Critical | Make grid separate for each level |  | 1 | 0.5 | Dylan | Not Started | Not Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Import new stage model | Replace the old model, optimise the grid to get a blance of enough lines to move on | 1 | 0.5 | Skye | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Decide on standard grid dimensions going forward |  | 1 | 1 | Dylan | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Restructure old levels using the grid based system | Chance here to also improve narrative and progressive teaching of mechanics, consider moving tangling earlier in the piece. | 6 | 2 | Angus | Not Started | Not Started | Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Critical | Create slingshotting mechanics | Tim knows what to do | 10 |  | Tim | Not Started | Not Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 1 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 2 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 3 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 1 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 2 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Not Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 3 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Not Started | Started | Started | Started | - | - | - | - | - | - | - | -
Critical | Filter Act 1 into only 3 best levels | Do as said | 4 |  | Angus | Not Started | Not Started | Not Started | Started | - | - | - | - | - | - | - | -
Critical | Make the gridded movement more tolerant | Junctions are a bit janky, have to ensure player is able to turn easily enough | 3 | 2 | Tim | Not Started | Not Started | Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Critical | Opening screen | Shows on startup, allows the players to enter the game. Provide smooth transitions between menu screen | 5 | 6.5 | Dylan | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Major | Create stage fire and stage water | Use cloths of different colours | 1 | 2 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Major | Create script to control which panels fo the stage will be deactivated for a given level | Use 2D array of "on" and "off" switches | 3 |  | Dylan | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Major | Choose which items should be brought on sideways | Add left or right option for where they can come in from for extra dynamics | 1 | 1 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Major | Make the vine prop killbox script into a prefab | Rename it to KillBox, make same size as single stage tile | 1 | 0.5 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Major | Make a clairvoyant mini grid around the characters | Displays the grid lines wherever they are even if raised in the y axis | 5 |  | Tim | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Major | Make quit button return to title screen | As stated | 1 | 0.5 | Harper | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Integrate Grid Movement into level switching | Each level will have it's own specific grid, so the level switcher will have to correctly load and unload each grid alongside the level. | 4 | 3 | Harper | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Make the camera start very zoomed in the first level | Better displays the characters and gets the player into the narrative, also can be used to teach about the strings and actually make sense cause they'll be able to read the puppets | 3 | 3 | Harper | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Bulk out the levels in each act | Add more props and general items as well as backdrop to enhance the stage effect, consider large set pieces specifically where any movement is supposed to be blocked: Don't just remove the grid points, put something physically in the player's way | 12 |  | Angus | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Major | Create Backdrops for each act/level | Lauren has a vision | 12 |  | Lauren | Not Started | Started | Started | Started | - | - | - | - | - | - | - | -
Major | Add colliders under mushrooms/tables | Anything that a player can walk undeneath should be blocked | 2 | 1 | Harper | Not Started | Not Started | Not Started | Started | Done (Needs Testing) | - | - | - | - | - | - | -
Major | Fix boxes moving through each other when grabbed | Hard cause I know to move them we disabled the collider, but has to be fixed |  |  | Tim | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Major | Select level button | Skips the level to any level, presumably across acts as well | 4 |  | Andrew | Not Started | Not Started | Started | Started | - | - | - | - | - | - | - | -
Major | Skip level button | Instantly skips the level from wherever you are | 0.5 | 0.5 | Dylan | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Major | Change dying image to something else | Show on gameover or when you complete | 2 |  | Dylan | Not Started | Not Started | Started | Done (Needs Review) | - | - | - | - | - | - | - | -
Major | Create breakable walls | Dennys to get wall from skye, break it in Maya | 2 |  | Dennys | Not Started | Not Started | Not Started | Started | - | - | - | - | - | - | - | -
Major | Closing screen | Show on gameover or when you complete | 2 |  | Dylan | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Minor | Fix the ground texturing | Remind skye to push the texturing | 1 |  | Skye | Not Started | Not Started | Not Started | Started | - | - | - | - | - | - | - | -
Minor | Add multiple directions stage props can move | All props move in from the top, add the option to move in from side and bottom | 1 | 1 | Harper | Not Started | Not Started | Not Started | Not Started | Done (Needs Testing) | - | - | - | - | - | - | -
Minor | Redo the game soundtrack and music effects | Scrap the old one or just keep the percussion and rebuild from there | 6 |  | Huw | Not Started | Not Started | Started | Started | - | - | - | - | - | - | - | -
Minor | Fix IK for climbing | Purely cosmetic, polish |  |  | Tim | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Minor | Restructure UI | Create better colour scheme, easier to read buttons, etc. | 4 |  | Dylan | Not Started | Started | Started | Started | - | - | - | - | - | - | - | -
Minor | Apply a bright front light to the initial zoom in | Illuminate the characters faces | 2 | 1 | Harper | Not Started | Not Started | Not Started | Started | Done (Needs Review) | - | - | - | - | - | - | -
Minor | Make objects kickable | Low tier, but will make the game environment much funner (LETS GOOOOOOO FOOTBALL MINIGAME WITH MUSHROOMS YEAHHH) | 4 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | -
Minor | Make "Take 1" sign appear at level start, same as when you die |  | 4 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | -
Minor | Create an advertising vid for socials |  | 8 |  | Angus | Not Started | Not Started | Not Started | Started | - | - | - | - | - | - | - | -
Minor | Add colliders to stage poles |  | 0.5 | 0.5 | Harper | Not Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Minor | Make puppets ragdoll | Make the puppets go limp when the stage transitions, anchor the puppets via the visual strings | 3 |  | Harper | Not Started | Not Started | Started | Started | Started | - | - | - | - | - | - | -
Minor | Make strings look like visual strings | You know | 2 |  | Tim | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Minor | Create actual assets for the anchor points | Could get spicy with them and add effects like, tilting as you move, pulling up when the character jumps | 4 |  | Skye | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Glowing eyes with slight trail |  | 2 |  | Dennys | Not Started | Not Started | Done (Needs Review) | - | - | - | - | - | - | - | - | -
Cosmetic | Shader for puppets when they go behind obstacles | Make them the same colour as the player, consider using plugin which makes it work | 2 |  | Dennys | Not Started | Not Started | Done (Needs Review) | - | - | - | - | - | - | - | - | -
Cosmetic | Restrict the camera pan | No jumping up, especially on player jumps | 1 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | -
Cosmetic | Recording clapping sound for sucessful level completion |  | 1 |  | Huw | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Make puppets do a little dance when they complete a level |  | 6 |  | Dennys | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Make the stage and scene react a bit more to completing the level | Make lights flash in foreground, sound off appluase plays, etc | 2 |  | Harper | Not Started | Not Started | Started | Started | - | - | - | - | - | - | - | -
Cosmetic | Use floating coloured spirit masks on goals to make them read better | Particle effects needed here as well as the actual model for each mask but made transparent | 3 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Particle effects on goals | Make the goals stand out more, passive particle effect and then an active particle effect when a player is standing in it | 0.5 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Enhance jumping particle effects | Make is easier to see, doesn't come through | 0.5 |  | Dennys | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Cosmetic | Consider using slower flicker script for stage lights | Use the script Dylan made for the into screen, currently light flicker is too fast and random | 1 |  | Harper | Not Started | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | -
Cosmetic | Create UI style for buttons | I'm sure lauren will have a vision | 3 |  | Lauren | Week 1: Not Started; Week 2: Not Started; Week 3: Not Started; Week 4: Started; Week 5: -
[5 empty] | Andrew | Week 1: Finished Item
Critical |  |  |  |  | Dylan | bar: Week 1
Major |  |  |  |  | Harper | Week 1: Not Started
Minor |  |  |  |  | Tim | Week 1: Started
Cosmetic |  |  |  |  | Dennys | Week 1: Done (Needs Testing)
[5 empty] | Skye | Week 1: Done (Needs Review)
[5 empty] | Huw | Week 1: Complete (Working)
Lauren
Angus
Note on O1: Dylan Jarvis: PAX

## Bug Tracking
Type | Description | When/Where Does it Happen | Reported By | Assignee | Status
Critical | Levers a bit sketch | String hook position moves, but upon dying, it does not move back, also lever doesn’t seem to reset | Dylan | Harper | Unfixed
Major | Lever positioning a bit sketch | On level with two levers which move you between the two houses still pretty sure the blue lever should move the red puppet and the red lever should move the blue puppet, also suffers from same issue above, also also, levers are a bit hard to acces due to being on that slightly lowered hedge, consider widening the building roof and just putting them next to the players | Dylan | Angus | Unfixed
Major | Can leave the grid unintentionally, and get stuck | Happens at corners near stage pillars, should be blocked from leaving the grid under any circumnstances | Dylan | Tim | Unfixed
Major | Sometimes player can sink into the floor | Generally happens after grabbing and moving a box, often happens on the first level with the well | Dylan |  | Unfixed
Minor | Can walk underneath table edge in first level | Collider is like a pentagon hexagon thing, we should aim for a cylinder if possible. | Dylan | Harper | Unfixed
Minor | Same as above for mushrooms | These are cones, not as bad cause it does kind of deflect the jump backwards, but worth checking if we want cylinders | Dylan |  | Unfixed
Minor | Occassionally string tangling does not unwind correctly | Undetermined, moving back and forth usually fixes the issue | Dylan |  | Unfixed
Minor | Small snap when switching between some lines | This only happens when moving in a negitive direction, either on X or Y, as the player jumps to a perpendicual line before continuing to travel along the one they are supposed to | Tim | Tim | Unfixed
Minor | Animation does not have a blended transition, makes the character look glitchy | Happens when the joystick is positioned exactly between the wlak and run animations | Dylan | Dennys | Unfixed
Minor | Consider which way the particles should be extending by default on the eyes | They kind of extend into the skull making the effect look strange when idle, consider extending outwards around the sides of the mask when idle: Perhaps even make the eyes slightly translucent and put a point light inside them to make the particle effects blend with the eyeball better | Dylan | Dennys | Unfixed
Critical | Restart not triggering, cannot manual restart or restart on death | Always | Dylan | Harper | Fixed
Critical | With the grid system, players stay snapped to grid between level transitions | Players have to effectively be deleted between levels to disconnect and restart, I think the respawn function can handle this easily, just needs to be activated in the right place | Dylan | Harper | Fixed
Critical | With the grid system, the players may be stuck on prior grid rather than finding the new grid with each level | Hopefully has to do with the same thing as above | Dylan | Harper | Fixed
Critical | Lever on mushroom level moves but does not actually execute its function | Straight forward | Dylan | Harper | Fixed
Major | Hiding the entire object of a level doesn't actually skip it | Left in an empty scene, also happens when you skip level 1 but level 2 is greyed out | Dylan | Harper | Fixed
Major | Climbing string made player invulnerable to being killed by vines | After climbing, happens because puppet changes layer so can't be hit by vines | Dylan | Dylan | Fixed
Major | Killbox working inconsistently on stage hazards | Water seems to have a collider blocking the hitbox, fire hazard hitbox not working at all | Dylan | Harper | Fixed
Critical |  |  | Dylan |  | Unfixed
Major |  |  | Harper |  | Working On
Minor |  |  | Tim |  | Fixed
Cosmetic |  |  | Dennys
Skye
Huw
Lauren
Angus

## Weekly Meeting Notes
Timeline
Who | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Tim | Working on recreating the movement engine to restrict movement only along the rails as discussed in class | Working on pulling and releasing, other puppets as well as levers. Complete changes to the strings to make grid based movement work. | Working on grid system, succesfully demonstrated proof of concept to Andy, was adopted moving forward. | Working on fixing a bug which involves movement issues, still working on making edge snapping more tolerant, slingshotting mechanic
Harper | Working on refactoring the level manager. Making object references more robust. Improved camera dynamics as well as lighting. | Making levers work, so the puppets are able to pull them. Play with ragdolling between level transitions. | Finalized new levers, lots of refactoring and tidying up the workspace. Started on puppet ragdoll and begun integration of new grid system. | Bugfixing the transition issue, polish the zoom in on level start mechanic
Dennys | Finished off most puppet animations needed for act 1 and 2. | Relearn Unity particle effect system to enhance environement effects and puppet particles. | Particle effects, start implementing from game, think about using the magic masks. Make the eyes glow with a slight trail. | Fix animation blend transistion between player walking and running, add glowing eye trail to puppets, find shader package to highlight characters going behind objects
Huw | Worked out how to do footsteps without making it sound bad. Using using wooden spoons. | Recording foosteps using the spoons. Figure out what to do to fix the soundtrack. Currently too tinny and simple. | Waiting for sound files, if not replied in 3 days, will start designing mp3 for level track. | Continue working on the soundtrack and score
Skye | Modify the stage to new specifications according to the grid change. | Finish act 2 props, start texturing them. Colab with Angus on socials. | Texture everything in act 2. Colab with Angus on socials. | Texture the stage floor, create a pulley asset for the string anchors, come up with a vision for the last three acts
Lauren | Started drawing background for backdrops, farm landscape, with house field, pond etc. Currently doing rough paper drafts. | Continue drafting backgrounds, finish backgrounds as if they've been handpainted. Started and completing marble statue prop with texture and UV. Buttons for UI. | Work on the marble model, continue working on the background models | Make some banners for the social vids, continue working on props, continue working on UI buttons
Dylan | Creating better documentation like this document as well as clarifying realistic scope for the rest of the semester. | Create an add player screen to make sure 2 player controllers are working. Redo all the UI stuff, add a skip level button. | Create an intro screen, rebuild UI so that it smoothly transitions | Create stage water aas a hazard, create stage fire as well
Angus | Slight edits on unity scenes, waiting for grid implementation to properly edit the stage. | Complete next act puzzles, definitely designed, ideally implemented in unity. Consider how to get exposure using a twitter or instagram social. | Rebuild the levels to work with the gridded movement | Condense act 1 into 3 levels, continue building levels for act 2
Andrew | - | - | Level selection screen, broken into 3 acts and 3 level boxes | -
Note on J2: Dylan Jarvis: PAX

## Usability Testing
Testing plan, plan what needs to be tested, iterate,
benchmark things like frames per second, structure a playtesting process
How many deaths per level, time taken, data driven decisions, what was favourite levels?
Least favourite levels, etc.

## Gantt Chart
Timeline
Events | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Production
Playable Game
Project Reporting
Programming
Movement Engine
Finalise Player Controller
Finalise Level Manager
Bug Fixing
Art
Finalise Models
Particle Effects
Socials
Design
Act 2 Scenes
Act 3 Scenes (pending)
Note on J2: Dylan Jarvis: PAX