## Task Tracking
Timeline
Who | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Tim | Timeline Week 1: Working on recreating the movement engine to restrict movement only along the rails as discussed in class; Timeline Week 2: Working on pulling and releasing, other puppets as well as levers. Complete changes to the strings to make grid based movement work.
Harper | Timeline Week 1: Working on refactoring the level manager. Making object references more robust. Improved camera dynamics as well as lighting.; Timeline Week 2: Making levers work, so the puppets are able to pull them. Play with ragdolling between level transitions.
Dennys | Timeline Week 1: Finished off most puppet animations needed for act 1 and 2.; Timeline Week 2: Relearn Unity particle effect system to enhance environement effects and puppet particles.
Huw | Timeline Week 1: Worked out how to do footsteps without making it sound bad. Using using wooden spoons.; Timeline Week 2: Recording foosteps using the spoons. Figure out what to do to fix the soundtrack. Currently too tinny and simple.
Skye | Timeline Week 1: Modify the stage to new specifications according to the grid change.; Timeline Week 2: Finish act 2 props, start texturing them. Colab with Angus on socials.
Lauren | Timeline Week 1: Started drawing background for backdrops, farm landscape, with house field, pond etc. Currently doing rough paper drafts.; Timeline Week 2: Continue drafting backgrounds, finish backgrounds as if they've been handpainted. Started and completing marble statue prop with texture and UV. Buttons for UI.
Dylan | Timeline Week 1: Creating better documentation like this document as well as clarifying realistic scope for the rest of the semester.; Timeline Week 2: Create an add player screen to make sure 2 player controllers are working. Redo all the UI stuff, add a skip level button.
Angus | Timeline Week 1: Slight edits on unity scenes, waiting for grid implementation to properly edit the stage.; Timeline Week 2: Complete next act puzzles, definitely designed, ideally implemented in unity. Consider how to get exposure using a twitter or instagram social.
Andrew | bar: Timeline Week 1 to Timeline Week 2
Note on J2: Dylan Jarvis: PAX