## Task Tracking
Type | Change | Description | Est. Time | Actual Time | Team Member | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Critical | Implement gridded movement system into the main branch | Use Tim's grid engine, must breif team on how to effectively use it when constructing levels | 8 |  | Tim | Not Started | Started | Done (Needs Testing) | - | - | - | - | - | - | - | - | -
Critical | Restructure old levels using the grid based system | Chance here to also improve narrative and progressive teaching of mechanics, consider moving tangling earlier in the piece. | 10 |  | Angus | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Critical | Import new stage model | Replace the old model, optimise the grid to get a blance of enough lines to move on | 1 |  | Skye | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 1 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 2 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 2 level 3 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 |  | Angus | Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 1 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 2 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Not Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Create Act 3 level 3 | Levels are to demonstrate more complexity, also requiring final capabilities | 4 |  | Angus | Not Started | Started | Started | - | - | - | - | - | - | - | - | -
Critical | Filter Act 1 into only 3 best levels | Do as said | 4 |  | Angus | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Critical | Make the gridded movement more tolerant | Junctions are a bit janky, have to ensure player is able to turn easily enough |  |  | Tim | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Critical | Opening screen | Shows on startup, allows the players to enter the game. Provide smooth transitions between menu screen | 5 | 6.5 | Dylan | Not Started | Started | Done (Needs Review) | - | - | - | - | - | - | - | - | -
Major | Make the camera start very zoomed in the first level | Better displays the characters and gets the player into the narrative, also can be used to teach about the strings and actually make sense cause they'll be able to read the puppets | 4 |  | Harper | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Major | Bulk out the levels in each act | Add more props and general items as well as backdrop to enhance the stag effect | 12 |  | Angus | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Major | Create Backdrops for each act/level | Lauren has a vision | 12 |  | Lauren | Not Started | Started | Started | - | - | - | - | - | - | - | - | -
Major | Add colliders under mushrooms/tables | Anything that a player can walk undeneath should be blocked | 2 |  | Harper | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Major | Fix boxes moving through each other when grabbed | Hard cause I know to move them we disabled the collider, but has to be fixed |  |  | Tim | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Major | Select level button | Skips the level to any level, presumably across acts as well | 4 |  | Andrew | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Major | Skip level button | Instantly skips the level from wherever you are | 0.5 | 0.5 | Dylan | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Major | Change dying image to something else | Show on gameover or when you complete | 2 |  | Lauren | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Major | Closing screen | Show on gameover or when you complete | 2 |  | Dylan | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Minor | Redo the game soundtrack and music effects | Scrap the old one or just keep the percussion and rebuild from there | 6 |  | Huw | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Minor | Fix IK for climbing | Purely cosmetic, polish |  |  | Tim | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Minor | Restructure UI | Create better colour scheme, easier to read buttons, etc. | 4 |  | Dylan | Not Started | Started | Started | - | - | - | - | - | - | - | - | -
Minor | Make objects kickable | Low tier, but will make the game environment much funner (LETS GOOOOOOO FOOTBALL MINIGAME WITH MUSHROOMS YEAHHH) | 4 |  | Harper | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Minor | Create an advertising vid for socials |  | 8 |  | Angus | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Minor | Add colliders to stage poles |  | 0.5 | 0.5 | Harper | Not Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Minor | Make puppets ragdoll | Make the puppets go limp when the stage transitions, anchor the puppets via the visual strings | 3 |  | Harper | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Minor | Make strings look like visual strings | You know | 2 |  | Tim | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Minor | Create actual assets for the anchor points | Could get spicy with them and add effects like, tilting as you move, pulling up when the character jumps | 4 |  | Skye | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Glowing eyes with slight trail |  | 2 |  | Dennys | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Cosmetic | Shader for puppets when they go behind obstacles | Make them the same colour as the player, consider using plugin which makes it work | 2 |  | Dennys | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Restrict the camera pan | No jumping up, especially on player jumps | 1 |  | Harper | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Recording clapping sound for sucessful level completion |  | 1 |  | Huw | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Make puppets do a little dance when they complete a level |  | 6 |  | Dennys | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Make the stage and scene react a bit more to completing the level | Make lights flash in foreground, sound off appluase plays, etc | 2 |  | Harper | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Use floating coloured spirit masks on goals to make them read better | Particle effects needed here as well as the actual model for each mask but made transparent | 3 |  | Dennys | Not Started | Not Started | Started | - | - | - | - | - | - | - | - | -
Cosmetic | Particle effects on goals | Make the goals stand out more, passive particle effect and then an active particle effect when a player is standing in it | 0.5 |  | Dennys | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Enhance jumping particle effects | Make is easier to see, doesn't come through | 0.5 |  | Dennys | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Cosmetic | Create UI style for buttons | I'm sure luaren will have a vision | 3 |  | Lauren | Not Started | Not Started | Not Started | - | - | - | - | - | - | - | - | -
Consider mid sem break, do we account for the time spent?
Consider bug testing time needed before pax, big playtesting
Andrew
Critical |  |  |  |  | Dylan | bar: Week 1
Major |  |  |  |  | Harper | Week 1: Not Started
Minor |  |  |  |  | Tim | Week 1: Started
Cosmetic |  |  |  |  | Dennys | Week 1: Done (Needs Testing)
[5 empty] | Skye | Week 1: Done (Needs Review)
[5 empty] | Huw | Week 1: Complete (Working)
Lauren
Angus
Note on O1: Dylan Jarvis: PAX

## Bug Tracking
Type | Description | When/Where Does it Happen | Reported By | Status
Major | Sometimes player can sink into the floor | Generally happens after grabbing and moving a box, often happens on the first level with the well | Dylan | Unfixed
Minor | Occassionally string tangling does not unwind correctly | Undetermined, moving back and forth usually fixes the issue | Dylan | Unfixed
Critical | Lever on mushroom level moves but does not actually execute its function | Straight forward | Dylan | Unfixed
Critical |  |  | Dylan | Unfixed
Major |  |  | Harper | Working On
Minor |  |  | Tim | Fixed
Cosmetic |  |  | Dennys
Skye
Huw
Lauren
Angus

## Weekly Meeting Notes
Timeline
Who | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Tim | Working on recreating the movement engine to restrict movement only along the rails as discussed in class | Working on pulling and releasing, other puppets as well as levers. Complete changes to the strings to make grid based movement work.
Harper | Working on refactoring the level manager. Making object references more robust. Improved camera dynamics as well as lighting. | Making levers work, so the puppets are able to pull them. Play with ragdolling between level transitions.
Dennys | Finished off most puppet animations needed for act 1 and 2. | Relearn Unity particle effect system to enhance environement effects and puppet particles. | Particle effects, start implementing from game, think about using the magic masks. Make the eyes glow with a slight trail.
Huw | Worked out how to do footsteps without making it sound bad. Using using wooden spoons. | Recording foosteps using the spoons. Figure out what to do to fix the soundtrack. Currently too tinny and simple. | Waiting for sound files, if not replied in 3 days, will start designing mp3 for level track.
Skye | Modify the stage to new specifications according to the grid change. | Finish act 2 props, start texturing them. Colab with Angus on socials. | Texture everything in act 2. Colab with Angus on socials.
Lauren | Started drawing background for backdrops, farm landscape, with house field, pond etc. Currently doing rough paper drafts. | Continue drafting backgrounds, finish backgrounds as if they've been handpainted. Started and completing marble statue prop with texture and UV. Buttons for UI.
Dylan | Creating better documentation like this document as well as clarifying realistic scope for the rest of the semester. | Create an add player screen to make sure 2 player controllers are working. Redo all the UI stuff, add a skip level button.
Angus | Slight edits on unity scenes, waiting for grid implementation to properly edit the stage. | Complete next act puzzles, definitely designed, ideally implemented in unity. Consider how to get exposure using a twitter or instagram social.
Andrew | - | - | Level selection screen, broken into 3 acts and 3 level boxes
Note on J2: Dylan Jarvis: PAX

## Gantt Chart
Timeline
Events | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Production
Playable Game
Project Reporting
Programming
Movement Engine
Finalise Player Controller
Finalise Level Manager
Bug Fixing
Art
Finalise Models
Particle Effects
Socials
Design
Act 2 Scenes
Act 3 Scenes (pending)
Note on J2: Dylan Jarvis: PAX