## Sheet1
Change | Team Member | Priority | Comment
Particle effects on goals | Dennys | Mid | Make the goals stand out more, passive particle effect and then an active particle effect when a player is standing in it
Enhance jumping particle effects | Dennys | Low | Make is easier to see, doesn't come through
Create UI style for buttons | Lauren | Mid | I'm sure luaren will have a vision
Restructure UI | Dylan | High | Officially confirming Andrew as dead weight
Fix boxes moving through each other when grabbed | Tim | Mid | Hard cause I know to move them we disabled the collider, but has to be fixed
Fix IK for climbing | Tim (later) | Mid | Purely cosmetic, polish
Skip level button | Dylan | High | Instantly skips the level from wherever you are
Opening screen | Dylan | High | Shows on startup.
Closing screen | Dylan | High | Show on gameover or when you complete
Player add screen | Dylan | High | Should show upon game start
Make objects kickable | Harper (later) | Low (very high) | Low tier, but will make the game environment much funner (LETS GOOOOOOO FOOTBALL MINIGAME WITH MUSHROOMS YEAHHH)
Create an advertising vid for socials | Angus/Skye | Mid
Add colliders to stage poles | Harper | Mid
Add colliders under mushrooms/tables | Harper | Mid | Anything that a player can walk undeneath should be blocked
Make strings look like visual strings | Tim | Mid | You know
Create actual assets for the anchor points | Skye/Lauren | Mid | Could get spicy with them and add effects like, tilting as you move, pulling up when the character jumps