## Task Tracking
Type | Change | Description | Est. Time | Actual Time | Team Member | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Major | Game needs a concluding moment | Curtains should close -> puppets come down and rat comes on -> all take a bow -> fade to black -> credits | 3 |  | Dylan | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Game needs a smoother intro | Consider changing the title screen so that it's embedded in the same scene, so when players press a button to start, the logo leaves, the curtains open and the game starts | 3 |  | Dylan | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Transition needs to be improved | Move puppets completely out of the stage, just "fuck them right off" - Andy | 1 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Make puppets ragdoll on death instead of dissappear | Hopefully harper still has most of the ragdol engine haha | 2 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Act 3 wallbreak cutscene and side-scrolling support | In final level of Act 2, puppets break the right wall. Act 3 is side-scrolling, so a lot of new code required. | 6 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Implement pulling animation for levers | Self explanatory | 1 |  | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Fix models for 2:2 | They just look like blocks of wood, specifically the cantilever platform over fire needs to go or cahnge (see below) | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Fix models for 2:2 | Cantilever bridge should move in when a lever is pulled (slide out of back wall or unfold from floor) | 1 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Fix models for 2:3 | Better model for breakable bridge, make it the same texture as the breakable walls or at least more clear that it can break | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Fix 3:1 layout | Move levers and breakable wall further right, consider moving red player anchor linearly inbetween blue anchor and wall so that the slingshot feels better | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Testing) | - | -
Major | Fix 3:2 | Make the box bigger: same height as the platform on the left | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Testing) | - | -
Major | Fix 3:2 | Make the platform on the left wider so that the box fits better, same for the higher right platform WIDEN | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Fix 3:2 | Put collider behind top right platform so players can't accidentally walk off the back (MAY BE FIXED BY ABOVE CHANGE, REVIEW LATER) | 1 |  | Angus | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Testing) | - | -
Major | Widen end goal hitboxes | Make it easier to trigger them so no need for little adjusment movements | 1 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Major | Constrain box movement to a single axis | While holding a box, can only move side to side, cause boxes only need to be moved side to side | 3 |  | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Minor | Improve celebration animations | Potentially make them variable, more than one animation and randomly pick between them | 1 |  | Dennys | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Balance the audio, make music quiter and bring sound effects louder | << | 1 |  | Dylan | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Implement the game sound FX | Footsteps, clapping, etc | 2 |  | Dylan | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Create+implement credits and title screen music | Huw is doing it I think | 3 |  | Huw | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Minor | Lever optimizing | Activate on turning in either direction, and only activate once per grab (so holding the lever after first activate won't activate it a second time) | 3 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Testing) | Done (Needs Testing) | - | -
Minor | Make objects kickable | Low tier, but will make the game environment much funner (LETS GOOOOOOO FOOTBALL MINIGAME WITH MUSHROOMS YEAHHH) | 4 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Minor | Make "Take 1" sign appear at level start, same as when you die |  | 4 |  | Harper | Not Started | Not Started | Not Started | Not Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Create an advertising vid for socials |  | 8 |  | Angus | Not Started | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Add rope for rat's "ratpel" motion | << | 2 |  | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Minor | Make puppets ragdoll | Make the puppets go limp when the stage transitions, anchor the puppets via the visual strings | 3 |  | Harper | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Make the rat stand in a place where players can't interact with him | <<< | 3 |  | Harper | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Have the rat leave after a period of time | Ideally he leaves after you do the thinhg that he's suggesting | 3 |  | Harper | Not Started | Not Started | Started | Started | Started | Started | Started | Started | Started | Started | - | -
Minor | Make strings look like visual strings | You know | 2 |  | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Cosmetic | Fix IK for climbing | Purely cosmetic, polish |  |  | Tim | Not Started | Not Started | Not Started | Not Started | Started | Started | Started | Started | Started | Started | - | -
Cosmetic | Restrict the camera pan | No jumping up, especially on player jumps | 1 | 1 | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Review) | Done (Needs Review) | - | -
Cosmetic | Recording clapping sound for sucessful level completion |  | 1 |  | Huw | Not Started | Not Started | Not Started | Not Started | Not Started | Started | Started | Started | Started | Started | - | -
Cosmetic | Consider using slower flicker script for stage lights | Use the script Dylan made for the into screen, currently light flicker is too fast and random, have turned it off to conserve performance | 2 |  | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | - | -
Cosmetic | Make the stage and scene react a bit more to completing the level | Make lights flash in foreground, sound off appluase plays, etc | 2 | 3 | Harper | Not Started | Not Started | Started | Started | Started | Done (Needs Review) | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | -
Critical | Implement that pulling the levers the other way brings the string anchor back to where it came from | Prevents soft lock, especially in the case where both levers are supposed to be pulled at the same time. | 2 | 1.5 | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | -
Critical | Scrap climbing system | Can't climb any more, holding grab button in air will hold puppet in vertical position infinitely, allowing them to swing, reintroduce the curved base while holding in air. As an extra thing, pressing grab button on the ground will have no effect, only if puppet is in the air. | 5 | 4.5 | Tim | Not Started | Not Started | Not Started | Not Started | Started | Started | Done (Needs Testing) | Complete (Working) | - | - | - | -
Critical | Create slingshotting mechanics | Tim knows what to do | 10 | 8.5 | Tim | Not Started | Not Started | Started | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | -
Critical | Make slingshotting break through wall | Tim knows what to do | 4 | 4 | Harper | Not Started | Not Started | Not Started | Not Started | Started | Started | Done (Needs Testing) | Complete (Working) | - | - | - | -
Critical | Create Act 2 level 1 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 | 4 | Angus | Started | Started | Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Critical | Create Act 2 level 2 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 | 3 | Angus | Started | Started | Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Critical | Create Act 2 level 3 | Levels are to demonstrate more complexity, also requiring slingshot capabilities | 4 | 3 | Angus | Started | Started | Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Critical | Create Act 3 level 1 | Assets need to be placed | 4 |  | Angus | Not Started | Not Started | Not Started | Started | Started | Started | Started | Complete (Working) | - | - | - | -
Critical | Create Act 3 level 2 | Assets need to be placed | 4 |  | Angus | Not Started | Not Started | Not Started | Started | Started | Started | Started | Complete (Working) | - | - | - | -
Critical | Create Act 3 level 3 | Assets need to be placed | 4 |  | Angus | Not Started | Not Started | Not Started | Started | Started | Started | Started | Complete (Working) | - | - | - | -
Critical | Filter Act 1 into only 3 best levels | Do as said | 4 | 2 | Angus | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Critical | Make the gridded movement more tolerant | Junctions are a bit janky, have to ensure player is able to turn easily enough | 3 | 2 | Tim | Not Started | Not Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Critical | Implement gridded movement system into the main branch | Use Tim's grid engine, must breif team on how to effectively use it when constructing levels | 8 | 9 | Tim | Started | Started | Complete (Working) | - | - | - | - | - | - | - | - | -
Critical | Make grid separate for each level |  | 1 | 0.5 | Dylan | Not Started | Not Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Import new stage model | Replace the old model, optimise the grid to get a blance of enough lines to move on | 1 | 0.5 | Skye | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Decide on standard grid dimensions going forward |  | 1 | 1 | Dylan | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Critical | Restructure old levels using the grid based system | Chance here to also improve narrative and progressive teaching of mechanics, consider moving tangling earlier in the piece. | 6 | 2 | Angus | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | -
Critical | Opening screen | Shows on startup, allows the players to enter the game. Provide smooth transitions between menu screen | 5 | 6.5 | Dylan | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Major | Implement animations for the following | Swing, slingshot being pulled, slingshot pulling, hanging (pose), run out of string at limit, victory | 4 | 4 | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | -
Major | Replace anchor point placeholder models with completed ones |  | 1 | 1 | Harper | Not Started | Not Started | Not Started | Not Started | Not Started | Started | Started | Complete (Working) | - | - | - | -
Major | Create script to control which panels fo the stage will be deactivated for a given level | Use 2D array of "on" and "off" switches | 3 | 4 | Dylan | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Major | Act Change cinematic | Curtains come in, flashy lights, etc | 4 |  | Harper | Not Started | Not Started | Not Started | Not Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | -
Major | Choose which items should be brought on sideways | Add left or right option for where they can come in from for extra dynamics | 1 | 1 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Major | Make the vine prop killbox script into a prefab | Rename it to KillBox, make same size as single stage tile | 1 | 0.5 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | -
Major | Make the magic shadow grid which renders on every level of the y axis | Displays the grid lines wherever they are even if raised in the y axis | 5 | 5.5 | Tim | Not Started | Not Started | Not Started | Not Started | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | -
Major | Create stage fire and stage water | Use cloths of different colours | 1 | 2 | Dylan | Not Started | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | -
Major | Make quit button return to title screen | As stated | 1 | 0.5 | Harper | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Integrate Grid Movement into level switching | Each level will have it's own specific grid, so the level switcher will have to correctly load and unload each grid alongside the level. | 4 | 3 | Harper | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Make the camera start very zoomed in the first level | Better displays the characters and gets the player into the narrative, also can be used to teach about the strings and actually make sense cause they'll be able to read the puppets | 3 | 3 | Harper | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | - | -
Major | Bulk out the levels in each act | Add more props and general items as well as backdrop to enhance the stage effect, consider large set pieces specifically where any movement is supposed to be blocked: Don't just remove the grid points, put something physically in the player's way | 12 | 15 | Angus | Not Started | Not Started | Not Started | Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | -
Major | Create Backdrops for each act/level | Lauren has a vision | 12 |  | Lauren | Not Started | Started | Started | Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | -
Major | Add colliders under mushrooms/tables | Anything that a player can walk undeneath should be blocked | 2 | 1 | Harper | Not Started | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | -
Major | Fix boxes moving through each other when grabbed | Hard cause I know to move them we disabled the collider, but has to be fixed |  |  | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | -
Major | Select level button | Skips the level to any level, presumably across acts as well | 4 | 6 | Andrew | Not Started | Not Started | Started | Started | Done (Needs Testing) | Done (Needs Testing) | Complete (Working) | - | - | - | - | -
Major | Skip level button | Instantly skips the level from wherever you are | 0.5 | 0.5 | Dylan | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Major | Change dying image to something else | Show on gameover or when you complete | 2 | 0.5 | Dylan | Not Started | Not Started | Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Major | Create breakable walls | Dennys to get wall from skye, break it in Maya | 2 |  | Dennys | Not Started | Not Started | Not Started | Started | Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | -
Minor | Fix the ground texturing | Remind skye to push the texturing | 1 |  | Skye | Not Started | Not Started | Not Started | Started | Complete (Working) | - | - | - | - | - | - | -
Minor | Add multiple directions stage props can move | All props move in from the top, add the option to move in from side and bottom | 1 | 1 | Harper | Not Started | Not Started | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Minor | Redo the game soundtrack and music effects | Scrap the old one or just keep the percussion and rebuild from there | 8 | 8 | Huw | Not Started | Not Started | Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Minor | Restructure UI | Create better colour scheme, easier to read buttons, etc. | 4 | 6 | Dylan | Not Started | Not Started | Started | Started | Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | -
Minor | Apply a bright front light to the initial zoom in | Illuminate the characters faces | 2 | 1 | Harper | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Minor | Add colliders to stage poles |  | 0.5 | 0.5 | Harper | Not Started | Done (Needs Testing) | Complete (Working) | - | - | - | - | - | - | - | - | -
Minor | Create actual assets for the anchor points | Could get spicy with them and add effects like, tilting as you move, pulling up when the character jumps | 4 |  | Skye | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Minor | Smooth line movement | Make switching lines smoother and respond to the player's predicted intentions rather than their literal inputs better | 2 | 2 | Tim | Not Started | Not Started | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | - | - | -
Cosmetic | Glowing eyes with slight trail |  | 2 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Shader for puppets when they go behind obstacles | Make them the same colour as the player, consider using plugin which makes it work | 2 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Make puppets do a little dance when they complete a level |  | 6 |  | Dennys | Not Started | Not Started | Not Started | Not Started | Done (Needs Review) | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Cosmetic | Use floating coloured spirit masks on goals to make them read better | Particle effects needed here as well as the actual model for each mask but made transparent | 3 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Particle effects on goals | Make the goals stand out more, passive particle effect and then an active particle effect when a player is standing in it | 0.5 |  | Dennys | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Enhance jumping particle effects | Make is easier to see, doesn't come through | 0.5 |  | Dennys | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | - | - | - | - | -
Cosmetic | Create UI style for buttons | I'm sure lauren will have a vision | 3 | 2.5 | Lauren | Not Started | Not Started | Not Started | Started | Done (Needs Review) | Complete (Working) | - | - | - | - | - | -
Cosmetic | Put some smoke particle effects around the stage | Picture like stage fog, so keep it low and sweeping | 1 | 1 | Dennys | Not Started | Not Started | Not Started | Not Started | Not Started | Done (Needs Review) | Complete (Working) | - | - | - | - | -
Cosmetic | Put some smoke particle effects coming from the fire | Make the fire more realistic | 1 | 0.5 | Dylan | Not Started | Not Started | Not Started | Not Started | Not Started | Complete (Working) | - | - | - | - | - | -
[5 empty] | Andrew | Week 1: Finished Item
Critical |  |  |  |  | Dylan | bar: Week 1
Major |  |  |  |  | Harper | Week 1: Not Started
Minor |  |  |  |  | Tim | Week 1: Started
Cosmetic |  |  |  |  | Dennys | Week 1: Done (Needs Testing)
[5 empty] | Skye | Week 1: Done (Needs Review)
[5 empty] | Huw | Week 1: Complete (Working)
Lauren
Angus
Note on O1: Dylan Jarvis: PAX

## Bug Tracking
Type | Description | When/Where Does it Happen | Reported By | Assignee | Status
Major | Levers being held after the anchor moves position goes back to original position | Thought this was fixed, but seems to be rebroken RIP | Dylan | Harper | Unfixed
Major | Levers can be grabbed through walls | Hard fix, leave it for now, consider shortening | Dylan | Harper | Unfixed
Major | Can grab box from on top of it | Not ideal as you can just surf the box, consider using a box colider which sticks out around character centre of mass, DOESN’T STICK OUT BEHIND | Dylan | Harper | Unfixed
Major | If you grab a player while they're falling they get stuck in frefall animation | Should be mostly fixed by the fix proposed above where the collider no longer allows you to grab shit above you | Dylan | Harper | Unfixed
Major | Player visual becomes displaced on Y axis | Seems to be related to grabbing your string and dying/respawning. | Harper | Tim | Fixed
Major | Player teleported down, under the stage and usually into the water kill boxes | Occurs usually when the players are tangled and one of the players jumps on top/close to the tangle point. | Harper | Tim | Fixed
Minor | Grabbing boxes is a bit janky | Particularly the 1-2 box. Maybe use a Hinge joint to connect the box to the puppet so it doesn't bounce around as much. | Harper | Harper | Unfixed
Minor | Loose strings look dodgy when swinging | Make them go tight while swinging | Dylan | Tim | Unfixed
Minor | The rat has a hat | Players can jump on the rat's head. Something to do with ground detection I think, make the ground raycasts ignore trigger colliders. | Harper | Harper | Fixed
Minor | 3-3 strings are too short to untangle on the final step of the level | The nature of the anchor points crossing over each other means you pretty much always get tangled and end up softlocked. | Harper | Angus | Unfixed
Minor | Player can pull and push the other player through obstacles |  | Harper | Tim | Unfixed
Minor | Occassionally string tangling does not unwind correctly | Undetermined, moving back and forth usually fixes the issue | Dylan | Tim | Working On
Cosmetic | Consider which way the particles should be extending by default on the eyes | They kind of extend into the skull making the effect look strange when idle, consider extending outwards around the sides of the mask when idle: Perhaps even make the eyes slightly translucent and put a point light inside them to make the particle effects blend with the eyeball better | Dylan | Dennys | Unfixed
Cosmetic | Untagling arrow gets difficult to see when raised cause its 2D | Pperhaps tilt it forward a few degrees, or make it a little pop-up like the contextual tutorials. | Dylan | Tim | Working On
Critical | Level 2:2 has a strange issue where you can beat the level by doing a cheeky string extension on player 1 | Underlying issue here is that you can move further than your normal string radius after you tangle. Not sure if this is localised to 1 level or a fundamnetal problem, but worth a look for sure | Dylan | Tim | Fixed
Critical | Grab button disabled when on ground | Shouldn't be able to grab your own string if you are groiunded, can only grab after a jump, this will help with only grabbing levers and other players on the ground | Dylan | Harper | Fixed
Critical | Act 2 Scene 2 breakable wall isn't breakable | I think it's something to do with BreakableProp.cs angle calculation, as it's the only wall placed horizontally in the game. All the others are vertical and work fine. | Dylan | Harper | Fixed | Requires some testing
Critical | Collider not being deleted after breakable prop is broken | Only sometimes, make walls break in 1 hit always, make bridge break in 2 hits always | Dylan | Harper | Fixed | Requires some testing
Critical | Restart not triggering, cannot manual restart or restart on death | Always | Dylan | Harper | Fixed
Critical | With the grid system, players stay snapped to grid between level transitions | Players have to effectively be deleted between levels to disconnect and restart, I think the respawn function can handle this easily, just needs to be activated in the right place | Dylan | Harper | Fixed
Critical | With the grid system, the players may be stuck on prior grid rather than finding the new grid with each level | Hopefully has to do with the same thing as above | Dylan | Harper | Fixed
Critical | Lever on mushroom level moves but does not actually execute its function | Straight forward | Dylan | Harper | Fixed
Critical | Levers a bit sketch | String hook position moves, but upon dying, it does not move back, also lever doesn’t seem to reset | Dylan | Harper | Fixed
Major | Glitchy swing | Pressing jump while holding onto string makes you go around the world | Dylan | Harper | Fixed
Major | First level can be beaten by just walking along ground | Shorten strings, otherwise I prefer it without hazards, it's nice | Dylan | Angus | Fixed
Major | Soft lock between books and chest of drawers | Level 2:1, leaves puppet in permanent fall state, books need to be moved slightly | Dylan | Angus | Fixed
Major | Generate momentum while holding the string | Swinging back and forth | Dylan | Tim | Fixed
Major | Inconsistant tangle changes when jumping over | Jumping over the other puppet while tangled provides somewhat inconsistant results, sometimes it updates the tangle by 1, other times it doesn't, leading to strange tangling behavior. | Tim | Tim | Fixed | Grid ded
Minor | Very small reverse snapping when switching between some lines | So ok hear me out, we no longer have snapping, we have *reverse snapping*, it's very small and scales with the directionChangeBoost, still something to do with the order of points, I can not figure it out | Tim | Tim | Fixed | Grid ded
Major | Make levers one shot | As soon as you crank them, they should go all the way, also ensure that cranking right sends it, and cranking left brings it back | Dylan | Harper | Fixed
Major | Level select button raycasting completely cooked | Can't seem to fix for some reason rip | Dylan | Dylan | Fixed
Major | Puppets position is not correctly set on respawn | If you die puppets should respawn exactly on their spawn, sometimes they maintain their position after death | Dylan | Harper | Fixed
Major | Boxes need gravity enabled | Enable the gravity so the boxes can fall into water and down cliffs. Make them kinematic so that bumping into them moves them a little, helps with soft lock boxes blocking ledges and shit | Angus | Harper | Fixed
Major | On level 4 pulling the lever can knock you off the rock | This happens in a few other spots as well, we need to reconsider design of these levels as well as potentially having a look at the physics of the levers, should we always put them in front of a grid point so the pulling doesn't hit you? Also, you can knock the lever down by running into it, consider making it "spring loaded" so it returns to a straight position | Dylan | Harper | Fixed
Major | Sometimes player can sink into the floor | Generally happens after grabbing and moving a box, often happens on the first level with the well | Dylan | Tim | Fixed
Major | Lever positioning a bit sketch, see above as well | On level with two levers which move you between the two houses still pretty sure the blue lever should move the red puppet and the red lever should move the blue puppet, also suffers from same issue above, also also, levers are a bit hard to acces due to being on that slightly lowered hedge, consider widening the building roof and just putting them next to the players | Dylan | Harper | Fixed | ?
Major | Can leave the grid unintentionally, and get stuck | Happens at corners near stage pillars, should be blocked from leaving the grid under any circumnstances | Dylan | Tim | Fixed
Major | Hiding the entire object of a level doesn't actually skip it | Left in an empty scene, also happens when you skip level 1 but level 2 is greyed out | Dylan | Harper | Fixed
Major | Climbing string made player invulnerable to being killed by vines | After climbing, happens because puppet changes layer so can't be hit by vines | Dylan | Dylan | Fixed
Major | Killbox working inconsistently on stage hazards | Water seems to have a collider blocking the hitbox, fire hazard hitbox not working at all | Dylan | Harper | Fixed
Minor | Can walk underneath table edge in first level | Collider is like a pentagon hexagon thing, we should aim for a cylinder if possible. | Dylan | Harper | Fixed
Minor | End of Game prevents switching to previous levels | Just gotta add support for it in the state machine and we're juicy you feel me | Angus | Harper | Fixed
Minor | Shards of broken walls can get in the way of visibility and movement |  | Angus | Harper | Fixed
Minor | Insides of broken walls are yellow | I can't believe Spongebob is fucking dead | Angus | Harper | Fixed
Minor | You can stand on top of where the lever used to be even after it's tilted away | Not a hug problem but worth having a look at | Dylan | Harper | Fixed
Minor | Small snap when switching between some lines | This only happens when moving in a negitive direction, either on X or Y, as the player jumps to a perpendicual line before continuing to travel along the one they are supposed to | Tim | Tim | Fixed
Minor | Same as above for mushrooms | These are cones, not as bad cause it does kind of deflect the jump backwards, but worth checking if we want cylinders | Dylan | Harper | Fixed
Minor | Animation does not have a blended transition, makes the character look glitchy | Happens when the joystick is positioned exactly between the wlak and run animations | Dylan | Tim | Fixed
Cosmetic | Curtain doesn't close completely on Act Change | I'll make the cloth physics more weighty so they close properly. | Angus | Harper | Fixed
Critical |  |  | Dylan |  | Unfixed
Major |  |  | Harper |  | Working On
Minor |  |  | Tim |  | Fixed
Cosmetic |  |  | Dennys
Skye
Huw
Lauren
Angus

## Weekly Meeting Notes
Timeline
Who | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Tim | Working on recreating the movement engine to restrict movement only along the rails as discussed in class | Working on pulling and releasing, other puppets as well as levers. Complete changes to the strings to make grid based movement work. | Working on grid system, succesfully demonstrated proof of concept to Andy, was adopted moving forward. | Working on fixing a bug which involves movement issues, still working on making edge snapping more tolerant, slingshotting mechanic | Fix the snapping glitch when walking down grid lines, created the clairvoyant grid, but it slows down the game too hard, trying to use a shadow effect to replicate the grid on raised z-axis. Fixing climbing IK. Scrap the climbing mechanic (refer to the prod doc) | Fixed snapping to junctions so it's a smaller snap. Lots of bug fixing, continuing working on scrapping climbing system, doing the grid visualisation and string visualisation.
Harper | Working on refactoring the level manager. Making object references more robust. Improved camera dynamics as well as lighting. | Making levers work, so the puppets are able to pull them. Play with ragdolling between level transitions. | Finalized new levers, lots of refactoring and tidying up the workspace. Started on puppet ragdoll and begun integration of new grid system. | Bugfixing the transition issue, polish the zoom in on level start mechanic | Pushed act changes, refining bugs, fixing stuff on the list. Act changes and transitions. | Implemented act changes, stage transitioning and cinematics. Finalising the transistions, start and end of level, end with celebration, start with UI clapper board for takes.
Dennys | Finished off most puppet animations needed for act 1 and 2. | Relearn Unity particle effect system to enhance environement effects and puppet particles. | Particle effects, start implementing from game, think about using the magic masks. Make the eyes glow with a slight trail. | Fix animation blend transistion between player walking and running, add glowing eye trail to puppets, find shader package to highlight characters going behind objects | Create a breakable wall asset or 2. | Added ambient dust to stage, try and do stage fog, breakable walls, play around with particle effects. Add backgrounds to each level.
Huw | Worked out how to do footsteps without making it sound bad. Using using wooden spoons. | Recording foosteps using the spoons. Figure out what to do to fix the soundtrack. Currently too tinny and simple. | Waiting for sound files, if not replied in 3 days, will start designing mp3 for level track. | Continue working on the soundtrack and score | Continue working on sountrack for act 2 and act 3 | Continue working on soundtrack stuff, act 2 and act 3 done.
Skye | Modify the stage to new specifications according to the grid change. | Finish act 2 props, start texturing them. Colab with Angus on socials. | Texture everything in act 2. Colab with Angus on socials. | Texture the stage floor, create a pulley asset for the string anchors, come up with a vision for the last three acts | Work on backstage room for act 3 levels where the breakout occurs | Made base model for breakable walls, worked on assignement, sarted modelling act 3 models. Tryhard the act 3 models and background
Lauren | Started drawing background for backdrops, farm landscape, with house field, pond etc. Currently doing rough paper drafts. | Continue drafting backgrounds, finish backgrounds as if they've been handpainted. Started and completing marble statue prop with texture and UV. Buttons for UI. | Work on the marble model, continue working on the background models | Make some banners for the social vids, continue working on props, continue working on UI buttons | UI buttons done, need to upload them. Continue working on props. Start on act 2 backdrop. | Rock HARD man. More props, finish backround for act 2. Working on production document.
Dylan | Creating better documentation like this document as well as clarifying realistic scope for the rest of the semester. | Create an add player screen to make sure 2 player controllers are working. Redo all the UI stuff, add a skip level button. | Create an intro screen, rebuild UI so that it smoothly transitions | Create stage water aas a hazard, create stage fire as well | Create script for making stage tile drop out and reveal the water underneath | Fuck all
Angus | Slight edits on unity scenes, waiting for grid implementation to properly edit the stage. | Complete next act puzzles, definitely designed, ideally implemented in unity. Consider how to get exposure using a twitter or instagram social. | Rebuild the levels to work with the gridded movement | Condense act 1 into 3 levels, continue building levels for act 2 | Continue developing act 2 and act 3 level implementation, | Reformatted act 1 levels, boiled it down to 3. Implemented act 2 level 1 and 2, bulk out the levels.
Andrew | - | - | Level selection screen, broken into 3 acts and 3 level boxes | - | Finshed level selector function | -
Note on J2: Dylan Jarvis: PAX

## Usability Testing
Type | Test Item | Defenition of Acceptable | Test Method | Qual/Quant | Result | Status
Critical | What levels do player's find most interesting/fun? | Most interesting levels are all represented in the PAX build | Survey conducted at playtesting events | Qualitative | Act 1 Level 7 (tangling to get ontop of well) | More Data Needed
Critical | What levels do player's find least interesting/fun? | Least interesting levels are not represented in the PAX build | Survey conducted at playtesting events | Qualitative | - | More Data Needed
Major | What levels do player's struggle the most on (time taken to complete)? | Hardest levels are presented as the last level of each act (or changed if they are too hard (>5 mins to complete)) | Reporting drawn from code after playtest | Quantitative | - | More Data Needed
Major | What levels do player's struggle the most on (number of deaths)? | Hardest levels are presented as the last level of each act (or changed if they are too hard (>20 deaths to complete)) | Reporting drawn from code after playtest | Quantitative | - | More Data Needed
Major | What levels do player's find the easiest (time taken to complete)? | Easiest levels are presented as the first levels of each act | Reporting drawn from code after playtest | Quantitative | - | More Data Needed
Major | What levels do player's find the easiest (number of deaths)? | Easiest levels are presented as the first levels of each act | Reporting drawn from code after playtest | Quantitative | - | More Data Needed
Critical |  |  |  | Qualitative |  | Unacceptable
Major |  |  |  | Quantitative |  | More Data Needed
Minor | [5 empty] | Acceptable
Cosmetic

## Performance Testing
Type | Test Item | Defenition of Acceptable | Test Method | Qual/Quant | Result | Status
Critical | Frame rate of the game | Doesn't drop below 30 for a period of longer than 2 seconds | Live monitoring during playtest session | Quantitative | Has not dropped below 30 frames over the course of the game | Acceptable
Major | Load time between scenes | Load time is not greater than 5 seconds | Live monitoring during playtest sessions | Quantitative | Load time is less than 5 seconds | Acceptable
Major | Memory usage
Major | Max object limit | Think of cloth on screen, chuck eveything on screen
Major | Checking for consistency across hardware
Major | Controller support
Critical |  |  |  | Qualitative |  | Unacceptable
Major |  |  |  | Quantitative |  | More Data Needed
Minor | [5 empty] | Acceptable
Cosmetic

## Gantt Chart
Timeline
Events | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Production
Playable Game
Project Reporting
Programming
Movement Engine
Finalise Player Controller
Finalise Level Manager
Bug Fixing
Art
Finalise Models
Particle Effects
Socials
Design
Act 2 Scenes
Act 3 Scenes (pending)
Note on J2: Dylan Jarvis: PAX